## Main Tracking
Salt Spring Island Administration Project Tracker |  |  |  | Report No. 4, 2020
Project | Description | Status | % | Comments | Timing
Priority Area: Drinking Water
Fulford Water Main Replacement | Replace a section of water main that crosses a creek, that has become exposed due to erosion. | In-Progress | 70 | Alternative options and budget amendement were approved in late 2020. CRD is finalizing the design and working on regulatory approvals. Expect to construct in Q1/Q2 of 2021. | Q2 2021
Cedars of Tuam Alternate Well Concept Design | Develop concept design, and order of magnitude cost estimate, to tie existing infrastructure into new well site, to increase water supply capacity, and improve quality. | Complete | 100 | Presented options and made recommendations for preferred option to proceed with detail design to connect a new well. Commission approved option in November of 2020
Beddis Intake Analysis | Intake assessment and designs for construction. | In-Progress | 80 | Assessment completed. Currently working on completing detailed design and specifications. | Q2 2021
Highland/Fernwood Intake Analysis | Intake assessment and designs for construction. | In-Progress | 80 | Assessment completed. Currently working on completing detailed design and specifications. | Q2 2021
Integrated Water Management Service Review - Water Optimization | Study to look at existing service structure around water management and service delivery; options for on-island management models | In-Progress | 95 | Draft being finalized for public release. | Q1 2021
Highland/Fernwood - DAF Float Waste Pump Design and Construct | Design and construct waste pump. | In-Progress | 30 | Staff has issued a Request for Proposal and will be reviewe proposal and fees and start the design process in Q1 of 2021. | Q3 2021
Highland (Legacy Service Area) | Highland Upper Reservoir Repair. | In-Progress | 30 | Currently conducting option analysis and repair versus replacement options and plans. Staff to bring the preferred option and budget to the Commission for approval. | Q3 2021
Highland (Legacy Service Area) | Demolish Abandoned Highlands Water Treatment Plant. | On-Hold |  | Dependent upon other service plan initiatives prioritized for 2020.
Highland/Fernwood Referendum | New intake construction and back-up power for water treatment plant. | On-Hold |  | Dependent upon other service plan initiatives prioritized for 2020.
Fulford Reynolds Road Strainer Facility | Demolish existing wooden building at the Reynolds Road Strainer Facility | Complete | 100 | Project completed in Q3 2020.
Fulford Water System Connection | Request to include a proposed development connected to the Fulford System | In-Progress | 60 | Draft impact study reviewed and feedback provided. Awaiting response from developer/consultant. | Q2 2021
Cedar Lane Water Licence | Apply a water license amendment for the Cedar Lane water service, due to regulatory requirement change. | Issue has arisen | 90 | Staff provided preliminary recommendations to the Commission and is communcating with the regulator for feedback. | Q2 2021
Priority Area: Sewer/Liquid Waste
Ganges sewer system rehabilitation | WWTP infrastructure upgrades. | Complete | 100 | Project largely complete with a few minor deficiencies awaiting resolution. | Q4 2020
Ganges WWTP Storage | Concept Design for Storage at Ganges WWTP. | In-Progress | 75 | Currently review preliminary design, analysis and cost estimates, as well as evaluating various options to optimize the construction of the storage/work area building. | Q2 2021
Ganges Hot stand-by SCADA System upgrade | update the SCADA for WWTP to be able to provide hot stand-by | In-Progress | 50 | Project delayed due to price escalation of SCADA system from Vender. Budget amendment has been submitted for review and approval. Expect to complete project by Q2 of 2021 once budget is approved. | Q2 2021
Maliview WWTP Upgrade Assessment | Engineering assessment, plant upgrade options, preliminary designs, cost estimates | Complete | 100 | Completed conceptual design and option analysis. | Q3 2020
Maliview WWTP Upgrade Detailed Design | Detailed design and cost estimation for upgrading of Maliview WWTP | In-Progress | 20 | Staff has applied for grant funding for this project. To issue a Request for Proposals for the detailed design project. | Q3 2021
Maliview Electoral Assent for Borrowing | Electoral assent for borrowing of funds for the upcoming Maliview WWTP Upgrading Project | In-Progress | 20 | Grant application for up to 90% funding submitted. Staff is to host public open house/consulation and conduct elector assent process. | Q3 2021
Rainwater Collection System for Burgoyne Bay sites | Design and install rainwater collection tanks and pipoing for Burgoyne Site | In-Progress | 90 | The system is installed in Q4 of 2020. Currently developing as built drawings and closing the project. | Q1 2021
Site Investigation for Burgoyne Bay Lagoons | Conduct phase 1 and phase 2 investigations for lagoon decommission at Burgoyne site | In-Progress | 75 | Completed Phase 1 investigation. Phase 2 field investigation plan and budget was approved by the Commission in Q4 2020. The CRD is currently planning for phase 2 work. | Q3 2021
Priority Area: Transportation
North Ganges Transportation Plan | Construct bike lanes and walking paths along Rainbow Rd, and Lower Ganges Rd, up to Upper Ganges Road (on non-Harbour side). | Complete | 100 | Construction completed in Q4 of 2020 | Q4 2020
Pathway: Phase 1 - Booth Canal to Central | Construct a multi-use trail along Lower Ganges Road, from Baker Road up to Vesuvius Bay Road. | Complete | 100 | Phase 1: construction is substentially completed. | Q4 2020
Pathway: Phase 2 - Booth Canal to Central | Construct a multi-use trail along Lower Ganges Road, from Booth Canal Road up to Baker Road. | In-Progress | 25 | Construction contract awarded by the CRD. Contractor is moblizing equipment and crew to site and construction clearing and grabbing are starting. Estimated completion by May/June 2020 unless delayed by weather. | Q2 2021
Fulford Ganges Hill | Pedestrian pathways and cycling design | In-Progress | 30 | MoTI completing detailed designs. CRD is working with MoTI to determine viability of cost sharing and construction of additional bike lane/pathway. | Q4 2021
Whims Road Pathway Survey and License | Survey Whims Road to Fernwood Road, apply and obtain License of Occupation from the Ministry | In-Progress | 25 | Project plan approved in 2020. The CRD will survey and submit application to MoTI as soon as funding is approved. | Q2 2021
Flexible Reflector Installation | Install flexible reflectors along pathways at Crofton and Blain Road | Operationalized | 50 | The CRD has obtained approval from MoTI ans is planning to install the reflectors as soon as materials are arrived. | Q1 2021
Merchants' Mews Pathway Design | Design a separate pathway along Upper Ganges Rd from Leisure Ln to Merchants Mews | In-Progress | 20 | Currently conducting preliminary site reviews and planning for a detailed design for this project. | Q4 2021
Transit Service Review | Review of transit service requisition to maintain annual increased operating expenses and growing service needs. | In-Progress |  | Remaining or new service expansion will require requisition increase. BC Transit conducting Salt Spring Island Transit Future Service Plan review.
Bus Shelter | Concept for project delivery of design and install artistic bus shelters. | In-Progress | 75 | Project delivery for design build for public art inspired bus shelters completed. Next steps SSI is consulting legal services and Commission and in the process of developing a guildline for project procurement and delivery of artistic bus shelters. | Q2 2021
Transportation Referendum | Referendum for Fulford Ganges Hill, and/or of Upper Ganges and Lower Ganges | On-Hold |  | Dependent upon capital planning projects identified by commission.
Priority Area: Parks and Recreation
Park Land:
Ganges Harbour Walk | A steering committee has been established to secure right of ways, develop designs and consult with the community to build the Ganges Harbour walk. | In-Progress |  | An application has been submitted to the Province to secure a right of way in front of the Ganges Marina. The Committee met Oct. 26, 2020 and has made a recommendation to PARC. This project will resume once additional staff capacity has been recruited. | Q4 2022
Parks Works Yard | Maintenance facility designs and costing | New |  | Dependent upon recruitment of additional capacity. Develop designs and costing. | Q4 2020
Parkland Acquisition | Purchase additional parkland for the purpose of playing fields | Issue has arisen |  | Unable to locate suitable land outside of ALR
Portlock Park Master Plan | Develop a master plan to reconfigure the park with the replacement of failing infrastructure | On-Hold |  | Dependent upon recruitment of additional capacity.
Fernwood Elementary Field Upgrade - Grant Application | Proposed enhancement project to upgrade Fernwood Elementary fields with two minor baseball, soccer practice, and walking perimeter track. | On-Hold |  | New grant application was submitted.
Community Parks:
Centennial Park Plaza | Upgrades to Centennial Park plaza | On-Hold | 5 | Dependent on recruitment of additional capacity. | Q4 2020
Trail Development - Trincomali | Development of a connector trail from Dunbabin Park to Trincomali Heights | In-Progress | 25 | Survey and environmental assessment now complete. Development of this new trail is moving ahead. | Q4 2020
Beach Access Improvements | Planned beach access upgrades in 2020 - Replace stairs at Baker Beach | In-Progress | 0 | Quotes are being received for alluminum stairs to replace wooden structure. | Q4 2020
Trail Upgrades - Mouat East | Continue to upgrade trail surface to allow for walkers, stroller and wheelchairs on urban trail | On-Hold | 0 | Work to be scheduled following completion of a number of other trail projects
Trail Upgrades -Drake to Bishop Walk | Upgrade trail drainage to prevent flooding | In-Progress | 25 | Designs complete. Procurement to begin Q1 2021. A grant application for $80,000 has been submited to the Covid Restart Funding grant. | Q2 2021
Duck Creek Parking | Designs and costing to be completed for additional parking at Duck Creek | On-Hold | 0 | Dependent upon recruitment of additional capacity planned.
Rotary Dock Replacement | Grant submitted to cover the costs of a larger replacement dock | Issue has arisen | 5 | Grant application was not successful, other funding options need to be explored.
Park Development (Pecks Cove) | $150,000 of community works funds were allocated the boardwalk studies and design. Any remaining project funds can be used towards the revitalization of this park | On-Hold | 0 | On hold until completion of boardwalk designs.
Fernwood Dock | Continue with maintenance and repairs as identified in the Condition Assessment report. | Complete | 100 | Safety ladder to be installed in 2020. Quotes received for ladder and installation. Installation completed 19/10/2020 | Q4 2020
Market Review | Review the operation and management of the Market in the Park | In-Progress | 10 | A business case is being prepared with recommendations for PARC's consideration | Q1 2021
Community Recreation:
Program Development | Develop additional programming for seniors, adults, and youth | In-Progress | 10 | New program offering are being provided with COVID-19 safety protocols | Ongoing
Pool:
Recreation Portable - Grant Application | Proposed portable for indoor recreation and licensed preschool programs at Rainbow Road aquatic center lands. | Complete | 100 | Grant approved. Modular installed and site prep and utility hook ups complete. Installed fence and playground to be completed. Licensed preschool opened 12/01/2020. | Q4 2020
Child Care Space Creation | Expand aquatic centre to include two multipurpose rooms, a universal washroom and storage room for licensed child care and recreation programs | In-Progress | 15 | Grant approved. Detailed designs have been developed and building permit submitted. | Q2 2022
Pool Electrical | Assessment of the condition of the electrical system | In-Progress | 5 | Assessment has been completed and so has a more detailed report with recommendations. Designs and costing being prepared to separate electrical room and electrical components. | Q3 2020
EV Charger | Second EV charger to be installed at the Rainbow Road Pool | In-Progress | 50 | Electrical work included with portable installation. ITQ posted for EV charger installation. | Q1 2021
Pool Site Master Plan | Development of a site master plan | On-Hold | 0 | Dependent upon recruitment of additional capacity planned. | Q4 2020
Priority Area: Economic Development
Regulatory Roadmap | Develop educational materials to support entrepreneurs navigate the development process. (Formerly called Red Tape Reduction) | In-Progress | 50 | Drafting content for an infographic/video for navigating the commercial development application process. Video content production on hold due to COVID. | Q3 2020
Shared Business Services Model | Develop a strategic business, operational and financial plan | In-Progress | 20 | Develop a strategic business, operational and financial plan for a shared business services entity to support small business, with a focus on goods producers in non-perishable food and beverage, artisan, and health and wellness sectors for rural island businesses. Grant extended to November 2021 and amended to apply new learning to the delivery of project. Contract awarded to Rural Island Economic Parntership to implment the grant terms.

## Lists
Status
Column1
New
In-Progress
On-Hold
Issue has arisen
Complete
Operationalized